## Slide 1: Using Reviews to Keep Projects on Track
Chapter 12

## Slide 2: Outline
In This Chapter
Discovering what new product reviews are for
Following the rules for a successful review
Saying no as a project reviewer
Running an effective review meeting
Creating a project’s business case

## Slide 3: Intro
Many things can change between management’s initial decision to resource a project and the time when the product development team has the product ready for market. You don’t want managers looking over the product development team’s shoulder, second-guessing and getting involved in the day-to-day or week-to-week decisions. On the other hand, you don’t want your team moving forward without the benefit of management’s wider and more strategic view, and its enthusiastic support.

## Slide 4: Intro
The solution is a reviewing process. At reviews, the product development team updates reviewers on the project status, and reviewers make decisions to supply necessary resources to projects to continue them through development to the next phase — or not.
At the heart of the review process is the business case. It gives the team a way to track key financial and strategic project parameters, and it gives members of management necessary project information that allows them to make “apples-to-apples” comparisons with other projects.

## Slide 5: Understanding the Purpose of Reviews

## Slide 6: Purpose of Reviews
In the product development process, NPD teams and their projects are char-tered (authorized, funded, or “given the go-ahead”) by management. This authorization happens early in a project’s lifecycle, in what people sometimes call the “fuzzy front end.”
From that point on, teams need to be adequately resourced and have autonomy. They should have the ability to be creative.

## Slide 7: Purpose of Reviews
However, NPD teams shouldn’t be so autonomous and so creative that they stray from the business case approved by management. Your company has to strike a balance and also be prepared to deal with unexpected roadblocks or changes in the business and strategic landscape.
What looked like a good project six months or a year ago may not seem like such a good bet today. That’s where the reviewing process comes in. In this section, we discuss the main purposes for reviews, and we describe when they should take place.

## Slide 8: Is the project still on track?

## Slide 9: Is the project still on track?
One big reason why you have to monitor new product projects as they go through the development process is to make sure they don’t migrate from the value propositions managers expect them to fulfill.
For this reason, companies divide the product development process into phases and punctuate the phases with reviews (or what some companies call gates or decision diamonds). Take a look at the Cheat Sheet in the front of the book to see the major phases and reviews.

## Slide 10: Is the project still on track?
During each phase, the development team has a chance to be autonomous and creative; at the reviews following each phase, management gets to see what the team is doing and assess whether the project is meeting the reviewers’ strategic and financial objectives (see the following section for financial issues).
The outcome of a review is like a contract between the team members and the reviewers. The reviewers, representing executives and managers, can give the team the resources and direction it needs to go through the next phase and to the next review.

## Slide 11: Does the project still make financial sense?

## Slide 12: Does the project still make financial sense?
When management approves a project, they base a significant part of their judgment on “What’s the return on our investment (ROI) likely to be?” Many companies use hurdles or thresholds — for example, the company might decide that it will seldom approve a project that won’t realize 15 percent over its cost.
Companies often hold reviews before project phases during which their investments will increase. For example, if the next phase requires expensive investments in special tooling or manufacturing infrastructure, management should make doubly sure that the project is worth the additional resources. This strategy is just good risk management — investing small amounts is okay, but when the sums get larger, the success criteria get firmer.

## Slide 13: Abiding by the Rules for a Successful Review

## Slide 14: Intro
Phase reviews in the product development process are an important part of what makes a company successful at developing new products. They are not informal meetings where “the folks” gather to shoot the breeze about the latest new technologies. They are formal occasions, and the best review ses- sions follow a few basic rules. But don’t let this stern warning keep you from enjoying your work! Formal occasions though they are, the best reviews are also places where people who know and respect each other can ask the hard questions and give deserved congratulations for jobs well done.

## Slide 15: Provide clear guidelines for team deliverables

## Slide 16: Provide clear guidelines for team deliverables
In order to grow your company’s competence in holding phase reviews, teams have to follow guidelines so that they prepare appropriately for the reviews. You can make two big mistakes regarding guidelines: leaving the guidelines unclear and overspecifying them. Good guidelines tell team members exactly what the reviewers need to know and what the team has to accomplish before a review for a phase is scheduled.

## Slide 17: Provide clear guidelines for team deliverables
Who creates these guidelines? It should be someone in management, because guidelines are effective and useful only insofar as they’re followed by a large majority of teams. In many companies, the executives appoint a process owner for NPD. The process owner’s responsibility is to manage the processes, includ-ing the review process. This person is also responsible for making sure that processes are changed over time, as his or her company learns what’s work- ing and what isn’t. (Check out Chapter 8 to find out more about the role of the process owner.)

## Slide 18: Provide clear guidelines for team deliverables
The following is an example of a deliverables checklist for a project that’s nearing the end of development. There’s another example in Figure 9-2 that you may want to look at. This checklist was used by a company that manufactured cameras. You’ll want to change the items to include the things that are important in your company. The cross-functional team leader (see Chapter 10) can use the checklist to manage the work of the team leading up to a review. After each item, write “by whom,” “by when,” and “percent complete.” When you’ve checked all or most of the items as “100 percent complete,” your team is ready for the review.

## Slide 19: Provide clear guidelines for team deliverables
❑ Beta Tests complete
❑ Pilot production runs complete; manufacturability confirmed
❑ Quality and reliability testing complete
❑ Product launch details complete and committed to by functions
❑ Market research that demonstrates market acceptance
❑ Comparison of manufacturing scale-up plan to marketing launch plan by region
❑ Proposal outlining key issues “cleaned up” and suggests who should be responsible and accountable for each
❑ Proposal outlining how we’ll measure product performance over time and who will be accountable for the measuring
❑ Initial order dates set and committed to by functions
❑ Action plan and request for resources needed to proceed to the next phase

## Slide 20: Train the reviewers to know what to look for

## Slide 21: Train the reviewers to know what to look for
Companies usually assume that their teams — the product developers — need the training on how to make reviews effective. This is true, but reviewers need review training, too. What reviewers expect, teams are likely to do. If your reviewers don’t know what to expect, though, trying to improve reviews by focusing on NPD teams is like carrying water uphill in a leaky bucket.
An executive should be responsible for making sure that reviewers are trained. The training doesn’t have to be a time sink for busy executives. With a well-thought-out plan, most reviewers will get what they need even if the training is limited to “JIT” (just-in-time training) that gives them what they need to know when they need to know it.

## Slide 22: Train the reviewers to know what to look for
When building a training program for reviewers, include an overview of the following points, at a minimum:
You need to know about the project under review before the phase review meeting so that you’re ready to make sound and informed deci- sions. If this means contacting functional members of the team before- hand, don’t hesitate. For example, if the project is developing technology that is of strategic significance for other projects, be sure to understand how all that is supposed to work.
You should know the role the project plays in your company’s overall new product portfolio, as well as the resource implications of the project for the new product pipeline. (See Chapter 11 for more on portfolios and pipelines.) You should understand the different types of reviews.

## Slide 23: Train the reviewers to know what to look for
You need to know when it’s appropriate to call a technical review, for example, instead of addressing technical issues at a phase review.
You should understand the purposes of the phase review, which are to determine the individual merits of a project and its ongoing fit with the company’s strategic objectives and to make a decision to continue, stop, or recycle a project (see the later section “For Reviewers: Knowing When and How to Say No”).

## Slide 24: Do the necessary team prep work

## Slide 25: Do the necessary team prep work
Your NPD team needs to complete many tasks to prepare for a phase review. Preparing for a review includes, but isn’t limited to, updating the business case and creating an executive summary. (You can read about the business case in Chapter 9, and we offer plenty more later in this chapter.
An executive summary covers all the information contained in the full report which the team will present at the review, but in condensed form. An execu- tive summary shouldn’t be longer than one or two pages. If your report has an outline or table of contents, follow that, and write short paragraphs. Write so that if a reviewer reads only the first sentence of each paragraph, she’ll still get the gist. o pro- vide a template in the Appendix.)

## Slide 26: Ensure complete review attendance

## Slide 27: Ensure complete review attendance
Having 100 percent attendance seems like a foregone conclusion, right? Not so fast. As companies and new product projects become more and more spread out, it becomes harder to bring a whole team and all the reviewers together for a productive hour of discussion and reflection (see the later sec- tion “Inviting the right people to the review” to see who should attend).
If you’re finding it difficult to gather all required review parties, try some approaches that other companies have found successful:

## Slide 28: Ensure complete review attendance
Set aside a time — perhaps one day per month — when all the reviews take place. If you have a set time, you can expect all the reviewers and the key members of the core NPD team to attend. The drawback of this method is that it can delay projects if your company has a hard stop at the end of each phase before the next phase can start. It works best if your reviews happen “around the time” of the transitions from one phase to the next.
Use videoconferencing to “gather” reviewers and teams. With video- conferencing, you can still display the team slides, the agenda, and any other necessary information for all the participants to see. Videoconfer- encing works well if your team members and your reviewers are dispersed, which is more and more the case these days.

## Slide 29: Ensure complete review attendance
Create rules of attendance. No one wants to be called out as the cause of project delay and a waster of company resources. Rules of attendance can instill this fear. At DuPont, for example, the PAC (Project Approval Committee) rules state that if more than one PAC member doesn’t show, the review is cancelled. A cancellation can significantly delay a project and upset a team. After DuPont put the rule in place, PAC members made sure they attended the sessions. One PAC member participated in a review from a telephone on the side of the road (he was on a bicycling vacation). Another joined a review from a cruise ship. It can work!

## Slide 30: Communicate review decisions

## Slide 31: Communicate review decisions
The reviewers’ decision during a phase review isn’t really a simple “go, stop, or redirect” decision. That final word is just the output of the decision-making process — the choice the reviewers make after they consider all the options, the information, the debate, and discussion. The decision-making process includes the following:
The reviewers’ assumptions, values, and concerns
What the reviewers know or find out about the project
What the reviewers understand about the new product portfolio and the resources that are available to the new product pipeline (see Chapter 11)
The reviewers’ takes on the company’s market strategy, their under- standing of the company’s competenci

## Slide 32: Communicate review decisions
The review is a conversation in which the team gets to understand the basis for a decision about a project. Team members also get to inform reviewers about their project and correct misunderstandings. The reviewers should walk away with a better understanding of the project; the team should walk away with a better understanding of exactly what reviewers are expecting and how their project aligns with the company’s NPD strategies.

## Slide 33: For Reviewers: Knowing When and How to Say No

## Slide 34: Intro
Businesspeople are supposed to be hardheaded and unsentimental, but for some reason, members of review committees often have a hard time saying no. Sometimes, we suspect, it’s because they aren’t sure that there are any better projects to replace the cancelled ones. If that’s a problem in your com- pany, read Chapter 5 for advice on how to come up with plenty of great options. Some executives really don’t understand that there’s room for only so many projects in the development pipeline. If your executives think this way, get them to read Chapter 11 on “Managing Your Corporation’s NPD Resources.” Whatever the reasons, make sure that the reviewers in your com- pany have a firm grasp on when they should cancel projects and on how they should do so. The following sections show you the way.

## Slide 35: When (and why) to stop projects

## Slide 36: When (and why) to stop projects
Here’s a list of appropriate times for reviewers to stop new product projects:
At the very beginning of the process: The concepts that you review during the Idea/Concept Screens (see Chapter 6) barely qualify as “pro- jects.” The team needs to present the review committee with many con- cepts to choose from. The ones that don’t make it into the development pipeline should hit the shelves for later or be licensed/sold if they have value that your company isn’t likely to use any time soon.
At the Feasibility Review (see Chapter 9): After a project passes through the Concept Review, the development team has many questions to answer, including the following:

## Slide 37: When (and why) to stop projects
  How long will it take to develop or acquire the needed technology, and how much will it cost?
  Will the proposed product appeal to a large enough market of customers?
  Will the margins be high enough for the company to make a good return on its investment?
The Feasibility Review is when reviewers and teams should weed out the projects that can’t answer yes to these questions. The best-run NPD processes look like funnels up to the Feasibility Review. After that point, you won’t mind if your process straightens out and looks more like a tunnel. Be sure, however, that the reviewers aren’t closing their eyes to problems that can occur after the Feasibility Review.

## Slide 38: When (and why) to stop projects
During the phase/review process: Reviewers have the opportunity to stop a project at scheduled reviews during the development process. For example, they can stop a project whenever
  The team and/or the reviewers determine that the project is so far out of bounds that it no longer makes good business sense to pursue it.
  You run into resource issues.
  Competitors have changed the basis of competition by introducing products that make the product your company is developing less attractive.
  Changes to the company’s new product strategy — usually expressed as a portfolio of products
Before or just after launch: No, not lunch. Launch. This should be a last resort. However, if the development team or the reviewers have reason to believe that their expectations for the product were way off, or if it looks like putting the product into market will harm the company’s brand or existing products, they should bite the bullet here instead of creating a bigger mess to clean up later.

## Slide 39: How to stop a project

## Slide 40: How to stop a project
Stopping a project is really as simple as saying to the team, “We’ve decided to stop your project.” The advice in this section centers on how to stop a pro- ject well – how to take care of team members, how to get value from can- celled projects, and so on.
First, management should take great care of the team. Next, management can turn its attention to the rejected project. You should try to extract all the
value that you can from a stopped project. This benefits a company in sev- eral ways, including helping the development team recognize that the com- pany values its work. The following list presents some possible sources of value from stopped projects:

## Slide 41: How to stop a project
  You may be able to sell or license any intellectual property (IP) you’ve developed (see Chapter 15 for more on IP).
  You can shelve the project if it seems like it may be worth developing in the future.
  You can make the customer visits and other market research the team carried out (see Chapter 4) available to other projects.
  You can divide the project’s resources or what the project has learned among other new product projects. This can be especially useful if a team member’s expertise is needed on other projects.

## Slide 42: Making Review Meetings Work

## Slide 43: Intro
Good new product phase reviews should be set up like any good business meeting.
They work best when the right people are in attendance, when every- one comes prepared, when the participants follow a clear agenda, and when all parties come away with a clear decision and goal to reach before the next review.
We take you through these requirements in the sections that follow.

## Slide 44: Inviting the right people to the review

## Slide 45: Inviting the right people to the review
The new product team leader(s) should attend every review, as should most or all of the members of the new product core team (see Chapter 10 for more on the team leader and the core and extended teams).
The team leader should invite any members of the extended development team whose specific knowledge the team needs in order to answer questions from the reviewers.

## Slide 46: Inviting the right people to the review
The other people who attend reviews are, of course, the reviewers. Reviewers are business and functional heads, managers, and executives who can assess the merits of the project under review while understanding the larger strategic landscape.
The reviewers oversee the resources that the team needs to keep the project going. Some companies call these people the Project Approval `Committee, or PAC.

## Slide 47: Following a clear meeting plan

## Slide 48: Following a clear meeting plan
A new product review meeting needs a clear agenda. It also helps if you have a facilitator who can lead the group and write key discussion points on a wall chart.
An hour is usually enough for presentation, discussion, and decision — but you don’t want to waste any of it. For more complex projects, a review may take up to two hours.

## Slide 49: Following a clear meeting plan
A review usually starts with the team leader or the review committee chair calling the meeting to order. The leader or chair reminds the attendees of the purpose of the meeting.
The purpose should be a simple variation on this theme: “The purpose of this meeting is to review the status of the X project, to address any questions the reviewers may have, and to come to a decision about the next phase of the project.”

## Slide 50: Following a clear meeting plan
The team then updates the reviewers —briefly— on events that have taken place since the last review and presents highlights of the business case.
Note: Usually, the team leader will do the presentation, with team members attend- ing in order to answer questions. However, if a part of the presentation is dicey and clearly in the lap of one of the functional members, he or she might present that part.

## Slide 51: Following a clear meeting plan
As part of its presentation, the team should make its recommendation to the reviewers to continue, hold, or stop the project.
You should also make the necessary decisions very explicit. When co-author Robin facilitated reviews, she would recommend that the teams have a slide at the beginning of their presentations entitled “Decisions Needed.”
The slide listed all the decisions needed at that review. The teams would show the same slides at the end of their presentations. Invite reviewers to ask questions at any time, but ask them to hold discussion until set points.
Design the presentation so that when you present something that probably needs discussion, you have a slide announcing that.

## Slide 52: Ending with a clear decision

## Slide 53: Ending with a clear decision
In some companies, reviewers send the new product team away after they’ve completed their questioning to give themselves a chance to discuss and decide alone.
Other companies complete the whole process with the teams and reviewers together. Be sure your participants are clear at the beginning of the meeting about how the decision-making process will unfold.
Companies also differ in how they make the decision. You can vote, in which case a simple majority wins, or you can work to consensus. It seems best to us that if any reviewer is firmly opposed to the majority decision, the team should do some further work to answer the questions that would allow the reviewers to come to consensus.

## Slide 54: Keeping review records

## Slide 55: The Prose of Finance and Strategy: Writing a Project’s Business Case

## Slide 56: Intro
In this section, we look at how a new product team moves from an early, preliminary business case to the full-fledged financial justification it will need as it moves into the Feasibility Review. We also explain how to update the business case as the team moves through the rest of the product development process

## Slide 57: Drafting the preliminary business case

## Slide 58: Drafting the preliminary business case
The new product team should draft a preliminary, mini business case (some- times referred to as a trigger document) as part of defining the product concept.
The preliminary business case outlines the requirements for the project and includes estimates of likely return. At this early stage, the team should use ranges — “The market for the product is between 100K and 300K,” for exam- ple. Ranges can accurately represent what the team can know at this point in the project.

## Slide 59: Drafting the preliminary business case
The best way to create a preliminary business case is to start with a docu- ment that asks for high-level estimates of what you’ll include in the full business case. Following are suggestions of what you might include in the preliminary business case:
  Project overview: Include a one-sentence project “mission” or value proposition, a brief description of the proposed project, and a brief description of the product that includes key customer requirements that the team has identified to date.
  Estimate of resources needed: Include the likely skills and material sup-port the team will need, and for how long. This is also the place to out- line possible supply-chain or partnership plans.

## Slide 60: Drafting the preliminary business case
  Strategic alignment: Include a statement of the project’s strategic importance and its alignment with the organization’s strategy.
  Project timing: Include the proposed launch date and a description of any known factors that might impact timing.
  Market overview: Include key segments and competitor information to the extent known.
  A brief description of technology to be included, plus any foreseen technology hurdles: Include important manufacturing and operations information here as well.
  Overview of legal, regulatory, and other issues: Include plans for addressing these to the extent known.
  Key parameters that will affect the financial value of the project: Include range estimates of sales units and volume, cost targets, margins, and market share.

## Slide 61: Drafting the preliminary business case
Be sure to include the names, team roles, and contact information of key team members, too.

## Slide 62: Factoring in project financials

## Slide 63: Factoring in project financials
At some companies, the business case is reduced pretty much to financials. If that’s the case in your company, we give you some good arguments at the end of this section as to why relying on financials alone isn’t such a good idea.
However, financials are very important. They’re based on estimates of market size and share, competitive assessments, and estimated selling prices. These estimates are part of your launch plan and should be included in the business case that the team prepares.

## Slide 64: Factoring in project financials
The following list presents some ways that companies judge the financial via- bility of their new product projects:
Net present value (NPV): The present value of cash inflows minus the present value of cash outflows (or minus initial investment in most cases). NPV is a standard method for financial evaluation of long-term projects — like NPD projects.
Internal rate of return (IRR): The return rate that a company expects to earn on the capital it invests. In general, if the IRR is greater than the project’s cost of capital, or hurdle rate, the project will add value for the company.
Earnings before interest and taxes (EBIT): Also known as operating income and operating profit. In deciding whether to invest in a new product project, executives some- times compare the firm’s existing earnings potential (or EBIT) with the profit potential of the investment.
Shareholder value added (SVA): Will the investment in a new product return more value to the company’s shareholders than it could earn in an alternative and safer investment such as risk-free bonds? If so, it will be an investment that produces a positive SVA.

## Slide 65: Factoring in project financials
This alphabet soup includes various ways that companies figure out the likely value of the projects they spend money on.
They all have to do with assess- ing the cost of capital — how much it really costs the company to spend its resources today on projects that will not yield results until some time in the future. Businesses, and their investors, tend to want their money now (if not yesterday). New product development forces them to use present money and resources for results that will come in the future.
New product teams have to show executives, shareholders, and reviewers that this makes good sense; the formulas in the previous list help to do that.

## Slide 66: Factoring in project financials
Computing/estimating the financials for your project
  To compute the financials for your project, you use a combination of estimates. The estimates usually include expected gross revenue, how much the prod- uct will cost to produce and distribute (cost of goods sold, or COGS), and other expenses. To figure your expected net revenue, you add the cost to develop the product, any capital expenses incurred, and usually some over- head charge.
Recognizing why companies shouldn’t become too fixated on financials
  Financials aren’t the whole story. Companies that rely too much on them tend to pull the risk out of their new product portfolios and end up falling behind as product developers.

## Slide 67: Factoring in project financials
Recognizing why companies shouldn’t become too fixated on financials
  The following list outlines a few problems with the world of project financials:
  Financial estimates can be very uncertain.
  The reason for launching a project may be strategic, not financial. For example,
    You may launch a product in order to block a competitor’s entry to a market.
    You may develop a product in order to build technological capac- ity or capability.
  Sometimes projects that don’t cost much but won’t return much either — for example, exploratory projects — can position a company for success downstream.

## Slide 68: Updating the prelims to draft the full business case

## Slide 69: Updating the prelims to draft the full business case
When you start with a preliminary business case that asks for the early version of information that you’ll include later, keeping the business case up-to-date becomes a normal part of your team’s activities.
In a business case update, your team should make clear exactly what elements have changed since the last review. The team is involved with the project nearly every waking moment (and in some sleeping ones, too) between reviews; the reviewers have had plenty of other tasks on their minds. You should provide a summary of changes to the business case as a part of the executive summary (see the earlier section “Do the necessary team prep work”).

## Slide 70: Updating the prelims to draft the full business case
Most business cases include three parts:
Program assumptions and resources: You cover the rationale for the NPD project, the key financial assumptions (see the previous section), an assessment of risks and uncertainties, and the team’s request for resources from the company’s different functions (see Chapter 11). The team should honestly tell reviewers what the risks and uncertain- ties of the project are, and the reviewers should be able to discuss these risks without blaming anyone. Being able to hold frank discussions of the business case is a good indication that your company has a culture in which new product development can thrive — a culture of openness, honesty, and respect.
Customer satisfaction, competitive landscape, and marketing plan: You include information about the target market, identified customer needs for the product (see Chapter 4), and the launch plan to date (see Chapter 13).
Product development and production plan: You provide the project schedule, including target review dates, your plans for research (if any), and your plans for working with partners and/or suppliers (see Chapter 16). You also include environmental issues, patent/legal issues, and stan- dards and quality issues in this part of the plan.

## Slide 71: Updating the prelims to draft the full business case
You can find a business case template in the Appendix to this book. Feel free to copy it just as it is, or tailor it to fit your organization’s needs.
A big part of the difference between the full business case and the preliminary business case is the thoroughness of the information that you should include. To create a preliminary business case, just weed out the more detailed stuff from the full case, and be sure to remind people to use estimates and ranges.

## Slide 72: Creating out-of-bounds criteria

## Slide 73: Creating out-of-bounds criteria
At the Feasibility Review of the development process (see Chapter 9), the review committee makes a decision about whether to fund a project, stick it on the shelf, toss it in the scrap heap, or try to sell it to someone else. The members base their decisions on the information the new product team pro- vides in its business case.
But what if things change? What if, for example, the target market is smaller than estimated, meaning that the company will sell fewer products than the development team was counting on? What if the time and resources neces- sary are much greater than anticipated? Or, what if it turns out that the tech- nology you had thought would take a year to develop can be acquired cheaply, driving your development time from years to months?

## Slide 74: Creating out-of-bounds criteria
During your Feasibility Review, you should specify certain changes that would affect the business case so seriously that the team would need to call an emer- gency review. The parameters you specify are known as out-of-bounds criteria.
To specify out-of-bounds criteria for a project, the team sets a range for how much the net present value (NPV, the value of the resources being spent on the project) can vary without making a huge difference to the business case. Other criteria include project schedule and expected return.

## Slide 75: Creating out-of-bounds criteria
By setting out-of-bounds criteria, the team members give the reviewers confi- dence that the product will be developed in a way that meets the review cri- teria and that the reviewers will be the first to know if that doesn’t happen — in time for corrective action, of course. This certainty also motivates review- ers to let projects move ahead without scheduled reviews, which speeds up the development process. As long as the team has set clear out-of-bounds crite- ria, increasing the speed won’t increase the risk.

## Slide 76: 谢谢