## Slide 1: Manajemen Proyek
Bab 03

## Slide 2: Outline
Global Company Profile: Bechtel Group
Visit: http://www.bechtel.com

## Slide 3: Outline
The Importance of Project Management
Project Planning
Project Scheduling
Project Controlling
Project Management Techniques: PERT and CPM
Determining the Project Schedule
Variability in Activity Times
Cost-Time Trade-offs and Project Crashing
A Critique of PERT and CPM
Using Microsoft Project to Manage Projects

## Slide 4: Learning Objectives
When you complete this chapter you should be able to:
Use a Gantt Chart for scheduling
Draw AOA and AON networks
Complete forward and backward passes for a project
Determine a critical path

## Slide 5: Learning Objectives
When you complete this chapter you should be able to:
Calculate the variance of activity times
Crash a project

## Slide 6: Bechtel Projects
Constructing 30 high-security data centers worldwide for Equinix, Inc. ($1.2 billion)
Building and running a rail line between London and the Channel Tunnel ($4.6 billion)
Developing an OIL PIPELINE from the Caspian Sea region to Russia ($850 million)
Expanding the Dubai Airport in the UAE ($600 million), and the Miami Airport in Florida ($2 billion)

## Slide 7: Bechtel Projects
Building liquid natural gas plants in Yemen ($2 billion) and in Trinidad, West Indies ($1 billion)
Building a new subway for Athens, Greece ($2.6 billion)
Constructing a natural gas pipeline in Thailand ($700 million)
Building 30 plants for iMotors.com, a company that sells refurbished autos online ($300 million)
Building a highway to link the north and south of Croatia ($303 million)

## Slide 8: Importance of Project Management
Bechtel Project Management
  International workforce, construction professionals, cooks, medical personnel, security
  Strategic value of time-based competition
  Quality mandate for continual improvement

## Slide 9: Importance of Project Management
Organizing Chaos
Managing Risk
Managing Quality
Managing Integration
Managing Change
Clearing Issues
Retaining and Using Knowledge
Learning From Failure

## Slide 10: Karakteristik Proyek
Unit tunggal
Terdiri dari banyak kegiatan yang saling berhubungan
Sulit utk direncanakan dan mengendalikan persediaan
Perlatannya bisa dipakai untuk berbagai tujuan
Memerlukan tenaga berketrampilan tinggi

## Slide 11: Project Characteristics
Waktu mulainya jelas
Waktu berkhirnya jelas
Memerlukan waktu panjang (dlm bulan atau tahun)
Kualitas produk sangat rendah
Variasi tugas sangat tinggi
Berbagai tugas sering saling terkait kinerjanya

## Slide 12: Project Characteristics
Organisasinya bersifat sementara
Sering merupakan bagian dari proyek besar
Tujuan dan karakteristik produk bisa jadi didefinisikan dan dicapai secara progresif
Hasilnya bisa jadi merupakan hasil dari beberapa unit proyek
Saling keterkaitan antara kegiatan yang satu dan lainnya mungkin rumit

## Slide 25: Project Definition
Proyek dapat didefinisikan sebagai serangkain kegiatan yang saling terkait yang diatur untuk mencapai hasil utama tertentu.
Proyek adalah kegiatan atau upaya yang unik dan dioperasikan sekali saja
Project adalah entitas sementara yang dibuat untuk mencapai output tertentu (biasanya berujud) sesuai dengan batasan-batasan waktu, biaya dan kualitas yang ditentukan terlebih dahulu.

## Slide 26: Activity Definition
Activity is an individual job or work effort requiring labor, resources and time, and is subject to management control.

## Slide 27: Program Definition
A program is a portfolio comprised of multiple projects that are managed and coordinated as one unit with the objective of achieving (often intangible) outcomes and benefits for the organization.

## Slide 28: Different between Project and Program
 | Project | Program
Objectives | Outputs – tangible; relatively easy to describe, define and measure; tending towards objective. | Outcomes – often intangible; difficult to quantify; benefits often based on changes to organizational culture and behaviors; introducing new capabilities into the organization; tending towards subjective.
Scope | Strictly limited; tightly defined; not likely to be subject to material change during the life of the project. | Not tightly defined or bounded; likely to change during the life cycle of the program.
Duration | Relatively short term; typically three to six months. | Relatively long term typically eighteen months to three years.
Risk profile | Project risk is relatively easy to identify and manage. The project failure would result in relatively limited impact on the organization relative to program risk. | Program risk is more complex and potentially the impact on the organization if a risk materializes will be greater relative to project risk. Programme failure could result in material financial, reputational or operational loss.
Nature of the problem | Clearly defined. | Ill-defined; often disagreement between key stakeholders on the nature and definition of the problem.
Nature of the solution | A relatively limited number of potential solutions. | A significant number of potential solutions with often with disagreement between stakeholders as to the preferred solution.
Stakeholders | A relatively limited number of stakeholders. | A significant number of diverse stakeholders; probable disagreement between them as to the definition of the problem & the preferred solution.
Relationship to environment | Environment within which the project takes place is understood and relatively stable. | Environment is dynamic; and programme objectives need to be managed in the context of the changing environment within which the organization operates.
Resources | Resources to deliver the project can be reasonably estimated in advance. | Resources are constrained and limited; there is competition for resources between projects.

## Slide 29: Different between Project and Program
 | Project | Program
Objectives | Outputs – tangible; relatively easy to describe, define and measure; tending towards objective. | Outcomes – often intangible; difficult to quantify; benefits often based on changes to organizational culture and behaviors; introducing new capabilities into the organization; tending towards subjective.
Scope | Strictly limited; tightly defined; not likely to be subject to material change during the life of the project. | Not tightly defined or bounded; likely to change during the life cycle of the program.
Duration | Relatively short term; typically three to six months. | Relatively long term typically eighteen months to three years.
Risk profile | Project risk is relatively easy to identify and manage. The project failure would result in relatively limited impact on the organization relative to program risk. | Program risk is more complex and potentially the impact on the organization if a risk materializes will be greater relative to project risk. Programme failure could result in material financial, reputational or operational loss.
Nature of the problem | Clearly defined. | Ill-defined; often disagreement between key stakeholders on the nature and definition of the problem.
Nature of the solution | A relatively limited number of potential solutions. | A significant number of potential solutions with often with disagreement between stakeholders as to the preferred solution.
Stakeholders | A relatively limited number of stakeholders. | A significant number of diverse stakeholders; probable disagreement between them as to the definition of the problem & the preferred solution.
Relationship to environment | Environment within which the project takes place is understood and relatively stable. | Environment is dynamic; and programme objectives need to be managed in the context of the changing environment within which the organization operates.
Resources | Resources to deliver the project can be reasonably estimated in advance. | Resources are constrained and limited; there is competition for resources between projects.

## Slide 30: Different between Project and Program
 | Project | Program
Objectives | Outputs – tangible; relatively easy to describe, define and measure; tending towards objective. | Outcomes – often intangible; difficult to quantify; benefits often based on changes to organizational culture and behaviors; introducing new capabilities into the organization; tending towards subjective.
Scope | Strictly limited; tightly defined; not likely to be subject to material change during the life of the project. | Not tightly defined or bounded; likely to change during the life cycle of the program.
Duration | Relatively short term; typically three to six months. | Relatively long term typically eighteen months to three years.
Risk profile | Project risk is relatively easy to identify and manage. The project failure would result in relatively limited impact on the organization relative to program risk. | Program risk is more complex and potentially the impact on the organization if a risk materializes will be greater relative to project risk. Programme failure could result in material financial, reputational or operational loss.
Nature of the problem | Clearly defined. | Ill-defined; often disagreement between key stakeholders on the nature and definition of the problem.
Nature of the solution | A relatively limited number of potential solutions. | A significant number of potential solutions with often with disagreement between stakeholders as to the preferred solution.
Stakeholders | A relatively limited number of stakeholders. | A significant number of diverse stakeholders; probable disagreement between them as to the definition of the problem & the preferred solution.
Relationship to environment | Environment within which the project takes place is understood and relatively stable. | Environment is dynamic; and programme objectives need to be managed in the context of the changing environment within which the organization operates.
Resources | Resources to deliver the project can be reasonably estimated in advance. | Resources are constrained and limited; there is competition for resources between projects.

## Slide 31: Examples of Projects
Building Construction
Research Project

## Slide 32: Examples of Projects
IT Dev Project
Water Treatment Project

## Slide 33: Examples of Projects
Waste Mgt Project
Bridge Construction Project

## Slide 34: Examples of Projects
Jakarta MRT Tunnel Project
Suramadu Bridge Construction Project

## Slide 35: Management of Projects
Planning - goal setting, defining the project, team organization
Scheduling - relate people, money, and supplies to specific activities and activities to each other
Controlling - monitor resources, costs, quality, and budgets; revise plans and shift resources to meet time and cost demands

## Slide 36: Project Management Activities
Planning
  Objectives
  Resources
  Work break-down structure
  Organization
Scheduling
  Project activities
  Start & end times
  Network
Controlling
  Monitor, compare, revise, action

## Slide 37: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 38: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 39: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 40: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 41: Project Planning, Scheduling, and Controlling
Figure 3.1
Budgets
Delayed activities report
Slack activities report
Time/cost estimates
Budgets
Engineering diagrams
Cash flow charts
Material availability details
CPM/PERT
Gantt charts
Milestone charts
Cash flow schedules

## Slide 42: Project Planning
Establishing objectives
Defining project
Creating work breakdown structure
Determining resources
Forming organization

## Slide 43
JAKARTA – BANDUNG FAST TRAIN

## Slide 46: Project Organization
Often temporary structure
Uses specialists from entire company
Headed by project manager
  Coordinates activities
  Monitors schedule and costs
Permanent structure called ‘matrix organization’

## Slide 47: Project Organization Works Best When
Work can be defined with a specific goal and deadline
The job is unique or somewhat unfamiliar to the existing organization
The work contains complex interrelated tasks requiring specialized skills
The project is temporary but critical to the organization
The project cuts across organizational lines

## Slide 48: A Sample Project Organization
Technician
Project No. 2
Project
Manager
Electrical
Engineer
Computer Engineer
Test
Engineer
Mechanical
Engineer
Project No. 1
Project
Manager
Technician
Marketing
Finance
Human
Resources
Design
Quality
Mgt
Production
President
Figure 3.2

## Slide 49: Matrix Organization
Marketing Operations Engineering Finance
Project 1
Project 2
Project 3
Project 4

## Slide 50: The Role of the Project Manager
Highly visible
Responsible for making sure that:
All necessary activities are finished in order and on time
The project comes in within budget
The project meets quality goals
The people assigned to the project receive motivation, direction, and information

## Slide 51: The Role of the Project Manager
Highly visible
Responsible for making sure that:
All necessary activities are finished in order and on time
The project comes in within budget
The project meets quality goals
The people assigned to the project receive motivation, direction, and information
Project managers should be:
Good coaches
Good communicators
Able to organize activities from a variety of disciplines

## Slide 52: Ethical Issues
Offers of gifts from contractors
Pressure to alter status reports to mask delays
False reports for charges of time and expenses
Pressure to compromise quality to meet schedules
Project managers face many ethical decisions on a daily basis
The Project Management Institute has established an ethical code to deal with problems such as:

## Slide 53: Work Breakdown Structure
Level
1. Project
2. Major tasks in the project
3. Subtasks in the major tasks
4. Activities (or “work packages”) to be completed

## Slide 54: Work Breakdown Structure
Level 4
Compatible with Windows 7
Compatible with Windows Vista
Compatible with Windows XP
1.1.2.3
1.1.2.2
1.1.2.1
(Work packages)
Level 3
Develop GUIs
Design Cost Tracking Reports
Module
Testing
Ensure Compatibility with Earlier Versions
Develop Cost/Schedule Interface
Defect
Testing
1.1.1
1.2.2
1.3.2
1.3.1
1.2.1
1.1.2
Figure 3.3
Level 2
Software Design
Cost Management Plan
System Testing
1.1
1.2
1.3
Level 1
Develop Windows 8 Operating System
1.0
Notes: GUIs = Graphical User Interfaces

## Slide 55: Project Scheduling Techniques
Ensure that all activities are planned for.
Their order of performance is accounted for.
The activity time estimates are recorded.
The overall project time is developed.

## Slide 56: Purposes of Project Scheduling
Shows the relationship of each activity to others and to the whole project
Identifies the precedence relationships among activities
Encourages the setting of realistic time and cost estimates for each activity
Helps make better use of people, money, and material resources by identifying critical bottlenecks in the project

## Slide 57: Project Management Techniques
Gantt chart
Critical Path Method (CPM)
Program Evaluation and Review Technique (PERT)

## Slide 58: A Simple Gantt Chart
Time
J F M A M J J A S
Design
Prototype
Test
Revise
Production

## Slide 59: Service For a Delta Jet
Figure 3.4
Passengers
Baggage
Fueling
Cargo and mail
Galley servicing
Lavatory servicing
Drinking water
Cabin cleaning
Cargo and mail
Flight services
Operating crew
Baggage
Passengers
Deplaning
Baggage claim
Container offload
Pumping
Engine injection water
Container offload
Main cabin door
Aft cabin door
Aft, center, forward
Loading
First-class section
Economy section
Container/bulk loading
Galley/cabin check
Receive passengers
Aircraft check
Loading
Boarding
0 10 20 30 40
Time, Minutes

## Slide 60: Project Controlling
Close monitoring of resources, costs, quality, budgets
Feedback enables revising the project plan and shift resources
Computerized tools produce extensive reports

## Slide 61: Project Management Software
There are several popular packages for managing projects
  Primavera https://www.oracle.com/applications/primavera/
  MacProject http://www.mac512.com
  MindView http://www.matchware.com
  HP Project http://www8.hp.com
  Fast Track http://www.aecsoftware.com
  Microsoft Project http://www.microsoft.com

## Slide 62: Project Control Reports
Detailed cost breakdowns for each task
Total program labor curves
Cost distribution tables
Functional cost and hour summaries
Raw materials and expenditure forecasts
Variance reports
Time analysis reports
Work status reports

## Slide 63: PERT and CPM
Network techniques
Developed in 1950s
  CPM by DuPont for chemical plants (1957)
  PERT by Booz, Allen & Hamilton with the U.S. Navy, for Polaris missile (1958)
Consider precedence relationships and interdependencies
Each uses a different estimate of activity times

## Slide 64: Six Steps PERT & CPM
Define the project and prepare the work breakdown structure
Develop relationships among the activities - decide which activities must precede and which must follow others
Draw the network connecting all of the activities

## Slide 65: Six Steps PERT & CPM
Assign time and/or cost estimates to each activity
Compute the longest time path through the network – this is called the critical path
Use the network to help plan, schedule, monitor, and control the project

## Slide 66: Questions PERT & CPM Can Answer
When will the entire project be completed?
What are the critical activities or tasks in the project?
Which are the noncritical activities?
What is the probability the project will be completed by a specific date?

## Slide 67: Questions PERT & CPM Can Answer
Is the project on schedule, behind schedule, or ahead of schedule?
Is the money spent equal to, less than, or greater than the budget?
Are there enough resources available to finish the project on time?
If the project must be finished in a shorter time, what is the way to accomplish this at least cost?

## Slide 68: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
A comes before B, which comes before C
(a)
A
B
C
B
A
C
A and B must both be completed before C can start
(b)
A
C
C
B
A
B
B and C cannot begin until A is completed
(c)
B
A
C
A
B
C

## Slide 69: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
C and D cannot begin until both A and B are completed
(d)
A
B
C
D
B
A
C
D
C cannot begin until both A and B are completed
D cannot begin until B is completed
A dummy activity is introduced in AOA
(e)
C
A
B
D
Dummy activity
A
B
C
D

## Slide 70: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
B and C cannot begin until A is completed
D cannot begin until both B and C are completed
A dummy activity is again introduced in AOA
(f)
A
C
D
B
A
B
C
D
Dummy activity

## Slide 71: AON Example
Table 3.1 | Milwaukee Paper Manufacturing’s Activities and Predecessors |  | 
ACTIVITY |  | DESCRIPTION | IMMEDIATE PREDECESSORS
A |  | Build internal components | —
B |  | Modify roof and floor | —
C |  | Construct collection stack | A
D |  | Pour concrete and install frame | A, B
E |  | Build high-temperature burner | C
F |  | Install pollution control system | C
G |  | Install air pollution device | D, E
H |  | Inspect and test | F, G

## Slide 72: AON Network for Milwaukee Paper
Start Activity
Activity A
(Build Internal Components)
Activity B
(Modify Roof and Floor)
Figure 3.5
C
A
Start
D
B

## Slide 73: AON Network for Milwaukee Paper
Activity A Precedes Activity C
Activities A and B Precede Activity D
C
A
Start
D
B
Figure 3.6

## Slide 74: AON Network for Milwaukee Paper
G
E
F
H
C
A
Start
D
B
Arrows Show Precedence Relationships
Figure 3.7

## Slide 75: AOA Network for Milwaukee Paper
H
(Inspect/ Test)
7
Dummy Activity
6
F
(Install Controls)
E
(Build Burner)
G
(Install Pollution Device)
5
D
(Pour Concrete/ Install Frame)
4
C
(Construct Stack)
1
3
2
B
(Modify Roof/Floor)
A
(Build Internal Components)
Figure 3.8

## Slide 76: Determining the Project Schedule
Perform a Critical Path Analysis
The critical path is the longest path through the network
The critical path is the shortest time in which the project can be completed
Any delay in critical path activities delays the project
Critical path activities have no slack time

## Slide 77: Determining the Project Schedule
KEGIATAN | PENJELASAN | WAKTU (MINGGU) | KEG YG MENDAHULUI
A | Membantun komponen internal | 2 | —
B | Modifikasi atap dan lantai | 3 | —
C | Membangun stak pengumpul | 2 | A
D | Cor beton | 4 | A, B
E | Membangun tungku pembakaran temmperatur tinggi | 4 | C
F | Memasang sistem pengendalian polusi | 3 | C
G | Memasang alat polusi udara | 5 | D, E
H | Pengawasan dan pengujian | 2 | F, G
 | Total waktu (minggu) | 25 | 

## Slide 78: Determining the Project Schedule
Perform a Critical Path Analysis
Earliest start (ES) = earliest time at which an activity can start, assuming all predecessors have been completed
Earliest finish (EF) = earliest time at which an activity can be finished
Latest start (LS) = latest time at which an activity can start so as to not delay the completion time of the entire project
Latest finish (LF) = latest time by which an activity has to be finished so as to not delay the completion time of the entire project

## Slide 79: Determining the Project Schedule
Activity Format
Figure 3.9
A
Activity Name or Symbol
Earliest Start
ES
Earliest Finish
EF
Latest Start
LS
Latest Finish
LF
Activity Duration
2

## Slide 80: Forward Pass
Begin at starting event and work forward
Earliest Start Time Rule:
If an activity has only a single immediate predecessor, its ES equals the EF of the predecessor
If an activity has multiple immediate predecessors, its ES is the maximum of all the EF values of its predecessors
ES = Max {EF of all immediate predecessors}

## Slide 81: Forward Pass
Earliest Finish Time Rule:
The earliest finish time (EF) of an activity is the sum of its earliest start time (ES) and its activity time
EF = ES + Activity time
Begin at starting event and work forward

## Slide 82: ES/EF Network for Milwaukee Paper
Start
0
0
ES
0
EF = ES + Activity time

## Slide 83: ES/EF Network for Milwaukee Paper
Start
0
0
0
A
2
2
EF of A = ES of A + 2
0
ES of A

## Slide 84: ES/EF Network for Milwaukee Paper
B
3
Start
0
0
0
A
2
2
0
3
EF of B = ES of B + 3
0
ES of B

## Slide 85: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 86: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
D
4
7
3
= Max (2, 3)

## Slide 87: ES/EF Network for Milwaukee Paper
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 88: ES/EF Network for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
Figure 3.10

## Slide 89: Backward Pass
Begin with the last event and work backwards
Latest Finish Time Rule:
If an activity is an immediate predecessor for just a single activity, its LF equals the LS of the activity that immediately follows it
If an activity is an immediate predecessor to more than one activity, its LF is the minimum of all LS values of all activities that immediately follow it
LF = Min {LS of all immediate following activities}

## Slide 90: Backward Pass
Begin with the last event and work backwards
Latest Start Time Rule:
The latest start time (LS) of an activity is the difference of its latest finish time (LF) and its activity time
LS = LF – Activity time

## Slide 91: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = EF of Project
15
13
LS = LF – Activity time

## Slide 92: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(LS of following activity)
10
13

## Slide 93: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(4, 10)
4
2

## Slide 94: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 95: Computing Slack Time
After computing the ES, EF, LS, and LF times for all activities, compute the slack or free time for each activity
Slack is the length of time an activity can be delayed without delaying the entire project
Slack = LS – ES or Slack = LF – EF

## Slide 96: Computing Slack Time
TABLE 3.3 | Milwaukee Paper’s Schedule and Slack Times |  |  |  |  | 
ACTIVITY | EARLIEST START ES | EARLIEST FINISH EF | LATEST START LS | LATEST FINISH LF | SLACK LS – ES | ON CRITICAL PATH
A | 0 | 2 | 0 | 2 | 0 | Yes
B | 0 | 3 | 1 | 4 | 1 | No
C | 2 | 4 | 2 | 4 | 0 | Yes
D | 3 | 7 | 4 | 8 | 1 | No
E | 4 | 8 | 4 | 8 | 0 | Yes
F | 4 | 7 | 10 | 13 | 6 | No
G | 8 | 13 | 8 | 13 | 0 | Yes
H | 13 | 15 | 13 | 15 | 0 | Yes

## Slide 97: Critical Path for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 98: ES – EF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 99: LS – LF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 100: Variability in Activity Times
CPM assumes we know a fixed time estimate for each activity and there is no variability in activity times
PERT uses a probability distribution for activity times to allow for variability

## Slide 101: Variability in Activity Times
Three time estimates are required
  Optimistic time (a) – if everything goes according to plan
  Pessimistic time (b) – assuming very unfavorable conditions
  Most likely time (m) – most realistic estimate

## Slide 102: Variability in Activity Times
Estimate follows eta distribution
Expected time:
Variance of times:
t = (a + 4m + b)/6
v = [(b – a)/6]2

## Slide 103: Variability in Activity Times
Estimate follows beta distribution
Expected time:
Variance of times:
t = (a + 4m + b)/6
v = [(b − a)/6]2
Probability of 1 in 100 of > b occurring
Probability of 1 in 100 of < a occurring
Probability
Optimistic Time (a)
Most Likely Time (m)
Pessimistic Time (b)
Activity Time
Figure 3.11

## Slide 104: Computing Variance
TABLE 3.4 |  | Time Estimates (in weeks) for Milwaukee Paper’s Project |  |  |  | 
ACTIVITY | OPTIMISTIC a |  | MOST LIKELY m | PESSIMISTIC b | EXPECTED TIME t = (a + 4m + b)/6 | VARIANCE [(b – a)/6]2
A | 1 |  | 2 | 3 | 2 | .11
B | 2 |  | 3 | 4 | 3 | .11
C | 1 |  | 2 | 3 | 2 | .11
D | 2 |  | 4 | 6 | 4 | .44
E | 1 |  | 4 | 7 | 4 | 1.00
F | 1 |  | 2 | 9 | 3 | 1.78
G | 3 |  | 4 | 11 | 5 | 1.78
H | 1 |  | 2 | 3 | 2 | .11

## Slide 105: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
s2 = Project variance
= (variances of activities on critical path)
p

## Slide 106: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
Project variance
s2 = .11 + .11 + 1.00 + 1.78 + .11 = 3.11
Project standard deviation
sp = Project variance
= 3.11 = 1.76 weeks
p

## Slide 107: Probability of Project Completion
PERT makes two more assumptions:
Total project completion times follow a normal probability distribution
Activity times are statistically independent

## Slide 108: Probability of Project Completion
Standard deviation = 1.76 weeks
15 Weeks
(Expected Completion Time)
Figure 3.12

## Slide 109: Probability of Project Completion
What is the probability this project can be completed on or before the 16 week deadline?
Z = – /sp
= (16 weeks – 15 weeks)/1.76
= 0.57
Due Expected date date of completion
Where Z is the number of standard deviations the due date or target date lies from the mean or expected date

## Slide 110: Probability of Project Completion
Z = – /sp
= (16 weeks – 15 weeks)/1.76
= 0.57
Due Expected date date of completion
What is the probability this project can be completed on or before the 16 week deadline?
.00 .01 .07 .08
.1 .50000 .50399 .52790 .53188
.2 .53983 .54380 .56749 .57142
.5 .69146 .69497 .71566 .71904
.6 .72575 .72907 .74857 .75175
From Appendix I
Where Z is the number of standard deviations the due date or target date lies from the mean or expected date

## Slide 111: Probability of Project Completion
Time
Probability (T ≤ 16 weeks) is 71.57%
Figure 3.13
0.57 Standard deviations
15 16 Weeks Weeks

## Slide 112: Determining Project Completion Time
Probability of 0.01
Z
Figure 3.14
From Appendix I
Probability of 0.99
2.33 Standard deviations
0
2.33

## Slide 113: Variability of Completion Time for Noncritical Paths
Variability of times for activities on noncritical paths must be considered when finding the probability of finishing in a specified time
Variation in noncritical activity may cause change in critical path

## Slide 114: What Project Management Has Provided So Far
The project’s expected completion time is 15 weeks
There is a 71.57% chance the equipment will be in place by the 16 week deadline
Five activities (A, C, E, G, and H) are on the critical path
Three activities (B, D, F) are not on the critical path and have slack time
A detailed schedule is available

## Slide 115: Cost–Time Trade-Offs and Project Crashing
It is not uncommon to face the following situations:
The project is behind schedule
The completion time has been moved forward
Shortening the duration of the project is called project crashing

## Slide 116: Factors to Consider When Crashing a Project
The amount by which an activity is crashed is, in fact, permissible
Taken together, the shortened activity durations will enable us to finish the project by the due date
The total cost of crashing is as small as possible

## Slide 117: Steps in Project Crashing
Compute the crash cost per time period. If crash costs are linear over time:
Crash cost
per period
=
(Crash cost – Normal cost)
(Normal time – Crash time)
Using current activity times, find the critical path and identify the critical activities

## Slide 118: Steps in Project Crashing
If there is only one critical path, then select the activity on this critical path that (a) can still be crashed, and (b) has the smallest crash cost per period. If there is more than one critical path, then select one activity from each critical path such that (a) each selected activity can still be crashed, and (b) the total crash cost of all selected activities is the smallest. Note that the same activity may be common to more than one critical path.

## Slide 119: Steps in Project Crashing
Update all activity times. If the desired due date has been reached, stop. If not, return to Step 2.

## Slide 120: Crashing The Project
TABLE 3.5 |  | Normal and Crash Data for Milwaukee Paper Manufacturing |  |  |  |  | 
ACTIVITY | TIME (WEEKS) |  |  | COST ($) |  | CRASH COST PER WEEK ($) | CRITICAL PATH ?
 | NORMAL |  | CRASH | NORMAL | CRASH |  | 
A | 2 |  | 1 | 22,000 | 22,750 | 750 | Yes
B | 3 |  | 1 | 30,000 | 34,000 | 2,000 | No
C | 2 |  | 1 | 26,000 | 27,000 | 1,000 | Yes
D | 4 |  | 2 | 48,000 | 49,000 | 1,000 | No
E | 4 |  | 2 | 56,000 | 58,000 | 1,000 | Yes
F | 3 |  | 2 | 30,000 | 30,500 | 500 | No
G | 5 |  | 2 | 80,000 | 84,500 | 1,500 | Yes
H | 2 |  | 1 | 16,000 | 19,000 | 3,000 | Yes

## Slide 121: Crash and Normal Times and Costs for Activity B
| | |
1 2 3 Time (Weeks)
$34,000 —
$33,000 —
$32,000 —
$31,000 —
$30,000 —
—
Activity Cost
Crash
Normal
Crash Time
Normal Time
Crash Cost
Normal Cost
Crash Cost/Wk =
Crash Cost – Normal Cost
Normal Time – Crash Time
=
$34,000 – $30,000
3 – 1
= = $2,000/Week
$4,000
2 Wks
Figure 3.15

## Slide 122: Critical Path and Slack Times for Milwaukee Paper
Figure 3.16
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0
Slack = 1
Slack = 1
Slack = 0
Slack = 6
Slack = 0
Slack = 0
Slack = 0
Slack = 0

## Slide 123: Advantages of PERT/CPM
Especially useful when scheduling and controlling large projects
Straightforward concept and not mathematically complex
Graphical networks help highlight relationships among project activities
Critical path and slack time analyses help pinpoint activities that need to be closely watched

## Slide 124: Advantages of PERT/CPM
Project documentation and graphics point out who is responsible for various activities
Applicable to a wide variety of projects
Useful in monitoring not only schedules but costs as well

## Slide 125: Limitations of PERT/CPM
Project activities have to be clearly defined, independent, and stable in their relationships
Precedence relationships must be specified and networked together
Time estimates tend to be subjective and are subject to fudging by managers
There is an inherent danger of too much emphasis being placed on the longest, or critical, path

## Slide 126: Using Microsoft Project
Program 3.1

## Slide 127: Using Microsoft Project
Program 3.2

## Slide 128: Using Microsoft Project
Program 3.3
Pollution Project Percentage Completed on Aug. 12 | 
ACTIVITY | COMPLETED
A | 100
B | 100
C | 100
D | 10
E | 20
F | 20
G | 0
H | 0

## Slide 129
Thank You so Much